    Quarterly Report Format (DTCC to STCC)
DISTRICT TOBACCO CONTROL CELL: CHAMPHAI DISTRICT
REPORT FOR THE QUARTER ENDING: 30th JUNE, 2016
PART-A 
	S. No
	Activities
	YES/NO
	Reasons, if the answer is No

	1.
	Whether District Cell has been set up 
	Yes
	

	2
	Status of recruitment of staff in the District Cell 
· District Consultant
	
Yes
	

	
	– Psychologist 
	Yes
	

	
	- Social Worker
	Yes
	

	
	- Data Entry Operator 
	Yes
	

	3
	Whether District Level Co-ordination Committee (DLCC) has been constituted 
	Yes, In the form of District Level Task Force (Tobacco Control)
	

	4.
	Whether District Level Monitoring Committee for Section – 5 of the COTPA has been constituted 
	Yes
	

	5.
	Whether COTPA and its rules have been displayed on the official district website 
	No  
	Champhai District does not have separate official district website 

	6.
	Whether challenging mechanism for COTPA has been set up at District Level
	Yes
	

	
	Whether separate head of account has been opened for deposit of challan amount at district level
	No
	Separate head of account is not opened at District level since challan can be deposited into the account head identified by Govt. of Mizoram for the whole state.

	
	Whether challan books have been received from STCC
	Yes
	

	
	Whether challan books have been distributed to authorized officers
	Yes
	

	
	Whether enforcement squads have been set up in the district to monitor compliance of COTPA 
	Yes
	

	
	Whether compliance of COTPA has been integrated in the monthly crime review meetings
	No
	Request has been made by us but action awaited from their  end 

	7.
	Whether Utilization Certificate has been submitted for the previous financial year
	No
	Provisional Utilization Certificate has been submitted to NHM Mizoram

	8
	Whether Statement of Expenditure has been submitted for the previous financial year 
	No
	Provisional Utilization Certificate has been submitted to NHM Mizoram




PART-B

	S.No
	Activities
	During the quarter 
	Up to the quarter in the Financial Year

	1.
	No. of meetings of the DLCC with dates
	0
	0

	2.
	Visits conducted by the enforcement squads 
	34
	34

	
	Persons challaned and amount collected (information to be given month-wise in the format as annexed )
	Section 4 COTPA: Offenders 09
Total No of fines 
Collected: Rs.450.00/-

	Section 4 COTPA: Offenders 09
Total No of fines 
Collected:Rs.450.00/-


	
	Complaint received through National Violations helpline
	None 
	None 

	
	Detail of such complaints where actions has been taken
	None 
	None 

	3.
	Training/sensitization programmes for different stakeholders organized by DTCC
	2

	2


	
	Participants in the trainings/sensitization programmes organized
	
	

	4.
	Types of IEC materials adapted/developed by DTCC (e.g. posters/stickers/handouts/wall paintings/hoardings etc)
	02
1. Hoarding
2. Wall Painting

	02

	5.
	PHCs, CHCs, Gov’t buildings, schools and other public places covered with these IEC materials
	33
	33

	6.
	Schools covered in the School Programme by the DTCC
(i) Public Schools
(ii) Private Schools
(iii) Coaching Institutes
	

24
12
00
Out of 36 schools 33 schools were covered without any cost incurred
	

24
12
00
Out of 36 schools 33 schools were covered without any cost incurred

	
	Details of children covered in the School Programmes
	3321
	3321

	
	Details of School Programmes conducted 
	Primary – 12
Middle – 14 
High School - 10
	Primary – 12
Middle – 14 
High School - 10

	7.
	Details of meeting held with other relevant State Govt. departments 
	11
1) Meeting was held with BDO, Ruantlang regarding Tobacco Free Village on 11th April 2016
2) Meeting was held with SDPO on 16th April 2016 regarding In-Service Training on Tobacco Control
3) Meeting was held with DC Champhai regarding Observation of WNTD on 21st May 2016
4) Meeting was held with Legal Metrology on 24th May 2016 regarding Joint Operation against Contraband Cigarettes
5) Meeting was held with 1st Class Magistrate regarding on-going cases under Section 7 of COTPA on 14th June 2016
6) Meeting was held on 14th June 2016 with Asst. Public Prosecutor court matters.
7) Meeting was held with BDO Ruantlang on 16th June 2016 regarding on-going activities for Tobacco Free Village
8)Meeting was held with DNO on 17th June 2016 regarding plan of action
9) Meeting was held with Deputy Medical Superintendent, Civil Hospital Champhai regarding TCC on 20th June 2016
10) Meeting was held with Deputy Commissioner on 20th June 2016 regarding implementation of Block Level Coordination Committee
11) Meeting was held with DNO on 28th June 2016 regarding upcoming quarterly review meeting
	11

	
	Details  of training programs of other departments in which DTCC participate and made presentations on tobacco control
	03
1) Participated in MHIP New Champhai Silver Jubilee celebration on 19th April 2016
2) Participated in Seminar on No Tobacco organized by United Pentecostal Church Khawzawl on 20th April 2016
3) Also participated in In-Service Training of Police Personnel of Champhai District on 26th May 2016
	03

	8.
	Details of meetings held with civil society organizations and professionals bodies (e.g. NGOs, NSS, NCC, IDA, IMA etc)
	03
1) Meeting was held with Bethel Fruit Grower Society
2) Meeting was held with Producer of Sudden Muanga Film
3) Meeting was held with VL Sahdah Nuai
	03

	9.
	No. of Blocks where Block Level Coordination Committee have been set up
	00

1
	00

1

	
	No of villages where Village Level Committee have been set up
	
	

	10.
	Details of TCCs set up in the district (Indicate separately details of TCCs set up in the district hospital, other government set-ups, NGOs,private set-ups,NGOs,private set ups etc)
	
TCC has been set up at District Hospital Champhai w.e.f July 2015
	
Nil

	
	a. Whether staff is in place in these TCCs
	Yes
	Yes

	
	b. Whether counselors working in these TCCs are formally trained in cessation activities ( indicate separately the total number of counselor in place and the number of counselors who have received formal training)
	
Yes
i. Total - 1
ii. Trained Counselor - 1
	Yes
i. Total -1
ii. Trained Counselor - 1

	
	c. Have the TCCs arranged for any cessation trainings for healthcare providers/workers? If yes, indicate the number of trainings undertaken with details.
	01 Training, 40 participants
	01 Training, 40 participants


	
	d. Whether pharmacological treatment of tobacco dependence is available
	Yes
	Yes

	
	e. Whether equipments such as Carbon Monoxide monitor and Spirometer have been procured
	No
	No

	
	f. No of persons who availed services at the TCCs 
	58
	288

	
	i) Number of persons who received counseling
	58
	288

	
	ii) Number of persons who received pharmacotherapy
	58
	288

	
	iii) Number of persons who received both
	58
	288

































	PART C

	Expenditure Details

	
	
	
	
	
	
	

	S.No
	Budgetary heads
	Opening Balance as on 01/04/2016
	Fund received 
	Total available funds
	Expenditure
	Closing Balance as on 31/06/2016

	DTCC

	1
	STAFF REMMUNERATION
	 
	 
	 
	 
	 

	
	One District Consultant 
	-40,000.00
	0.00
	-40,000.00
	120,000.00
	-160,000.00

	
	One Social Worker 
	-25,000.00
	0.00
	-25,000.00
	75,000.00
	-100,000.00

	2
	TRAINING
	 
	0.00
	0.00
	 
	 

	
	District level Trainning/ Sensitization Programmes
	-8,000.00
	0.00
	-8,000.00
	19,500.00
	-27,500.00

	
	Trainings on Tobacco Cessation for Health Care Providers
	-764.00
	0.00
	-764.00
	19,000.00
	-19,764.00

	
	Others
	-2,256.00
	0.00
	-2,256.00
	18,500.00
	-20,756.00

	3
	IEC
	 
	0.00
	0.00
	 
	 

	 
	IEC Materials (posters/
handouts/hoardings, media campaign etc)
	0.00
	0.00
	0.00
	0.00
	0.00

	4
	SCHOOL PROGRAMME
	 
	 
	 
	 
	 

	
	Conduct of awareness programmes in schools
	-399,200.00
	0.00
	-399,200.00
	24,700.00
	-423,900.00

	
	Others
	0.00
	0.00
	0.00
	0.00
	0.00

	5
	MONITORING
	 
	0.00
	0.00
	 
	 

	
	Mobility of enforcement squad and related expenditures
	-11,105.00
	0.00
	-11,105.00
	0.00
	-11,105.00

	
	Others
	0.00
	0.00
	0.00
	0.00
	0.00

	6
	PHARMACOLOGICAL TREATMENT
	 
	 
	 
	 
	 

	
	Procurement of drugs and related expenditures
	7,506.00
	0.00
	7,506.00
	22,931.00
	-15,425.00

	7
	FLEXIPOOL
	-12,000.00
	0.00
	-12,000.00
	97,826.00
	-109,826.00

	8
	INFRASTRUCTURE
	 
	 
	 
	 
	 

	 
	One time grant for Office Establishment(computer with printer/accessories etc)
	5,378.00
	0.00
	5,378.00
	0.00
	5,378.00

	9
	Earned Bank Interest (In any)
	2,279.00
	2,187.00
	4,466.00
	0.00
	4,466.00

	 
	TOTAL
	-483,162.00
	2,187.00
	-480,975.00
	397,457.00
	-878,432.00

	TCC

	1
	STAFF REMUNERATION
	 
	 
	 
	 
	 

	
	One Psychologist
	-25,000.00
	0.00
	-25,000.00
	75,000.00
	-100,000.00

	2
	INFRASTRUCTURE
	 
	 
	 
	 
	 

	
	One time grant (Procurement of equipment etc)
	0.00
	0.00
	0.00
	0.00
	0.00

	3
	Training and outreach
	0.00
	0.00
	0.00
	0.00
	0.00

	4
	Contingency and Misc
	7,091.00
	0.00
	7,091.00
	0.00
	7,091.00

	5
	Earned Bank Interest (If any)
	0.00
	0.00
	0.00
	0.00
	0.00

	 
	TOTAL
	-17,909.00
	0.00
	-17,909.00
	75,000.00
	-92,909.00

	 
	GRAND TOTAL
	-501,071.00
	2,187.00
	-498,884.00
	472,457.00
	-971,341.00



Note: Rs. 4,56,065/- was taken as a temporary loan from NHM, Mizoram through State Tobacco Control Cell.
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Signature & Seal
District Nodal Officer





















 












Total No. of Challans and Fines Collected
Month & Year: April 2016 
	
Name of the District



	

Section IV

	

Section V

	

Section VI

	

Section VII

	Cumulative for all Sections


	
	No. Of Challans
	Fines collected
	No. Of Challans
	Fines collected
	No. Of Challans
	Fines collected
	No. Of Challans
	Fines collected
	No. Of Challans
	Fines collected

	CHAMPHAI
	02
	Rs.100
	00
	00.00
	00
	00.00
	00
	00.00
	02
	Rs.100.00






Total No. of Challans and Fines Collected
Month & Year: May 2016 
	
Name of the District



	

Section IV

	

Section V

	

Section VI

	

Section VII

	Cumulative for all Sections


	
	No. Of Challans
	Fines collected
	No. Of Challans
	Fines collected
	No. Of Challans
	Fines collected
	No. Of Challans
	Fines collected
	No. Of Challans
	Fines collected

	CHAMPHAI
	00
	₹ 00.00
	00
	₹ 00.00
	00
	₹ 00.00
	00
	₹ 00.00
	00
	₹ 00.00






Total No. of Challans and Fines Collected
Month & Year: June 2016
	
Name of the District



	

Section IV

	

Section V

	

Section VI

	

Section VII

	Cumulative for all Sections
(4 & 7)


	
	No. Of Challans
	Fines collected
	No. Of Challans
	Fines collected
	No. Of Challans
	Fines collected
	No. Of Challans
	Fines collected
	No. Of Challans
	Fines collected

	CHAMPHAI
	07
	Rs.350
	00
	₹ 00.00
	00
	₹ 00.00
	00
	₹ 00.00
	07
	Rs.350.00
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